Development of production-grade ETL Pipeline for Databricks (PySpark + ADLS)

Objective:

The objective of this project is to design and implement a generic, scalable solution for ingesting and standardizing Excel data across multiple systems, with the ability to extend to new systems in the future.

Assumption:

Large Volume of Data are in several systems as below-

~30 GB across 8 systems, each system 2–8 GB, with ~4 years worth of excel files

This is how the folder is organized

Historyfolder/system/year/system2019

Within each file there are sheets, some files we might need to ingest two sheets.

Timeline (Approximately 12–16 Weeks)

The entire assignment is divided into tentative 7 phases as given below. The timeline is dynamic in nature and therefore, some of the phases may consume more than the allocated time.

Phase 1: Setup & Discovery (Weeks 1–2)

- Repo, configs, and Git setup.

- Mount ADLS to Databricks workspace.

- Build file inventory (“inventory.file_inventory”).

- Run header detection + normalization on sample files.

Deliverable: First report of normalized headers for all 12 files.

Phase 2: Mapping & Canonicalization (Weeks 3–4)

- Create mapping table (~67 canonical fields).

- Business SME sessions to confirm mappings across 7 systems.

- Drift detection prototype (“schema_drift” Delta table).

Deliverable: Initial conformed schema + mapping draft.

Phase 3: Bronze Layer (Weeks 5–6)

- Implement Excel -> parquet ingestion.

- Write bronze ingestion job (with metadata: filename, system, year/month).

- Populate audit.ingestion_log.

Deliverable: All 12 files loaded into Bronze (ADLS/Delta).

Phase 4: Silver Layer + DQ (Weeks 7–9)

- Apply mappings to Bronze -> Silver.

- Type casting + DQ checks (“dq_logs”).

- Resolve duplicate columns handling.

Deliverable: Silver tables with canonical schema across all 7 systems.

Phase 5: Drift Engine & Monitoring (Weeks 10–11)

- Automate schema drift logging (“audit.schema_drift”).

- Add dashboards (Databricks SQL / Power BI).

- Configure alerts for ingestion failures & drift events.

Deliverable: Drift reports + monitoring dashboard.

Phase 6: Backfill & QA (Weeks 12–13)

- Run one-time backfill for all historic 30 GB.

- Validate row counts, mapping accuracy, DQ exceptions.

Deliverable: Backfilled Bronze & Silver, validation logs.

Phase 7: Documentation & Handover (Weeks 14–16)

Write runbook + mapping change playbook.

- Train client team on:

- how to update mappings,

- how to review drift reports,

- how to re-run ingestion/backfill jobs.

Deliverable: Final signed-off solution + handover.

Summary

| Phase | Weeks | Dates | Actual Completion Date |
| --- | --- | --- | --- |
| Setup & Discovery | 1–2 | Oct 6 – Oct 19, 2025 | Oct 20, 2025 |
| Mapping & Canonicalization | 3–4 | Oct 20 – Nov 2, 2025 |  |
| Bronze Layer | 5–6 | Nov 3 – Nov 16, 2025 |  |
| Silver + DQ | 7–9 | Nov 17 – Dec 7, 2025 |  |
| Drift & Monitoring | 10–11 | Dec 8 – Dec 21, 2025 |  |
| Backfill & QA | 12–13 | Dec 22, 2025 – Jan 4, 2026 |  |
| Documentation & Handover | 14–16 | Jan 5 – Jan 25, 2026 |  |